## Dark
PROJECT TITLE
The Hive Tracker |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project Start Date: | 2022-05-15 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling Increment: | 0 | time axis 2022-05-15 to 2022-07-09
Milestone description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
TITLE 1
Control System | On Track | Name | 30% | 2022-05-15 | 45
Computing System | Low Risk |  | 60% | 2022-05-15 | 45
Mechanical Design | Med Risk |  | 50% | 2022-05-15 | 45
Power & Propulsion System | On Track |  | 80% | 2022-05-15 | 45
Spraying Mechanism | High Risk |  | 30% | 2022-05-15 | 45
Social Media Outreach | On Track |  | 40% | 2022-05-15 | 45
To add more data, Insert new rows ABOVE this one