## Dark
PROJECT TITLE
Control & Computing System Tracker |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project Start Date: | 2022-05-15 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling Increment: | 0 | time axis 2022-05-15 to 2022-07-09
Milestone description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
TITLE 1
Select Control Software | On Track | Name | 100% | 2022-05-15 | 45
Image Processing (helipad) | Low Risk |  | 100% | 2022-05-15 | 45
Path Optimization | Med Risk |  | 20% | 2022-05-15 | 45
Select Microcontroller | On Track |  | 50% | 2022-05-15 | 45
Select MicroComputer | High Risk |  | 30% | 2022-05-15 | 45
Select GPS Tracking System | On Track |  | 50% | 2022-05-15 | 45
Select Environment Sensors | On Track |  | 20% | 2022-05-15 | 45
Optimize for Aerodynamic Design of Drone | Med Risk |  | 0% | 2022-05-15 | 45
SITL Simulations | Low Risk |  | 90% | 2022-05-15 | 45
To add more data, Insert new rows ABOVE this one